## Sheet1
Sr. # | Tasks | Status | Remarks
1 | Regions Form (Adding Fileds for Executive Director and Executive VP) | Done
2 | Sites Form (Adding Fileds for PGM ) | Done
3 | Adding Columns in Sites Table | Done
4 | Adding Filters in Sites Form | Done
5 | Created a new form for Site next outages | Done | New Form
6 | Changing Form of SiteEquipment | Done
7 | Adding Columns in Site Equipments | Done
8 | Adding Filters for Site Equioments | Done
9 | Bringing Outages from Sites Next outages and mapping with site Equipments | Done
10 | Assigning Insurance and TILS based on Site Access(Pending) |  | Need discussion
11 | Documentation Library for sites (Pending) |  | New Form
12 | Adding Missing columns for TILS | Done
13 | TIL number , and target date should be displayed and to be part of filtering. | Done
14 | Status should be in text instead of numbers such as (closed/in progress/ open). | Working
15 | Once an evidence is attached it doesn’t get saved.
16 | Changes in fields does not get saved after hitting save.
17 | Filtering doesn’t work when changes has been done in status. For example If a line item status changed to closed. When I use the filter option and select filter by closed. It doesn’t work. |  | Issue in TIL's or Insurance
18 | In TIL tracker report, it would be good if the TIL document is available for download for reference
19 | Suggestion: calStatus/calcPriority/budgetCalc/ddtCalc/evidenceCalc/implementationCalc/partsCalc/sapCalc should be removed from display as these should be only in background. |  | Need discussion
20 | Suggestion: it would be good if an action item is assigned to a person, it notifies him in email.
21 | Suggestion: attachment icon should only appear if there is an attachment.
22 | Once the tracker is downloaded, it is better all hidden fields are added as part of the extract. |  | Need discussion
23 | Suggestion: a visual representation of overall closure will be great.
24 | Owner of each recommendation missing
25 | Days to target to be added. |  | Need discussion
26 | Is there a possibility to Link it to Power BI
27 | Evidence uploaded or no to be given automatically |  | Need discussion
28 | Closing date of actions to be given automatically |  | Need discussion
29 | For me I think that it will be great if we could Follow all other audits and ongoing actions in the same system |  | Need discussion
30 | Structure of the report extracted( possibility to chose what to have in the report same that we do in Synergi Life) |  | Need discussion
31 | Why not to use Synergi for Tils, Insurance and Internal Audit follow-up? |  | Need discussion